## Financial Summary
Project Reset Financial Summary
Category | Item | Estimated Cost (Low) | Estimated Cost (Base) | Estimated Cost (High) | Potential Benefit (Base)
Scope Redefinition
| Cost-Benefit Analysis | 1000 | 2000 | 3000 | 5000
| Budget Reallocation | 0 | 0 | 0 | 0
Critical Deliverables
| Game Code Valuation | 5000 | 10000 | 15000 | 0
| IP Protection | 2000 | 4000 | 6000 | 0
Revised QA Checkpoints
| QA Process Redesign | 1500 | 3000 | 4500 | 7500
| Automated Testing Tools | 3000 | 6000 | 9000 | 10000
| Dedicated QA Personnel (Est. 1 month) | 5000 | 8000 | 12000 | 15000
Total Estimated Costs
Total Potential Benefits

## Risk Assessment
Project Reset Risk Assessment
Risk Category | Risk Description | Probability (1-5) | Impact (1-5) | Risk Score (P x I) | Mitigation Action
Execution Risk | Core Integration Delay | 4 | 5 |  | CTO action needed; dedicated resources.
Execution Risk | Marketing Content Gaps | 3 | 4 |  | Dedicated content resources required.
Financial Risk | QA Recurrence / Rework Costs | 3 | 4 |  | Implement revised QA checkpoints, budget for automated testing.